## Instructions
The provided checklist is designed to assist the user with general installation guidance and pre-inspection quality control.
Refer to manufacturer's installation instructions for product specific information which may supercede the information given here.
See DrJ Engineering for additional Educational Programs

## Checklist
Revised 7/7/2020
Items to be Checked | Installer | Building Official | Comments
FPIS Attributes
Compliance with ANSI/SBCA FS100, where wind pressure resistance is required
Framing
Wall is square and true.
Stud spacing, blocking, and bracing requirements are met.
FPIS Installation
FPIS boards aligned with bottom edge of wall.
Boards trimmed at all window and door openings.
All framing covered with FPIS
Joints fit tightly
Vertical seams not visible from interior.
All damaged areas repaired per manufacturer’s instructions.
Fastening (Direct attachment or through furring):
Fastener spacing per manufacturer’s instructions (1) Around edges of panel (2) Through panels and into interior members
Fasteners are flush and snug.
No overdriven or underdriven nails.
Water-Resistive Barrier (WRB):
Code compliant WRB and required flashing provided.
If FPIS is used as a WRB: all joints, openings, and penetrations sealed per manufacturer’s installation instructions.